Project Budget

| Budget Item | Description | Cost |
| --- | --- | --- |
| Onsite 3 Day Staff Training by developers of HEAT Program. | 10 Probation and CBO Partner staff to be trained, materials, supplies, per diem costs, and associated travel expenses | 15,000 |
| Onsite Fidelity and Quality Control Coaching by Program Developers | 4 onsite Coaching and Feedback sessions to ensure program implementation fidelity | 12,800 |
| Program Implementation - 50 adult clients, 25 youth clients | Workbooks, Supplies, Incentives, Transportation, Service and Advocacy Projects, Completion Ceremonies. | 25,500 |
|  |  | Total: 53,300 |
| In Kind Contributions including Probation Staff and Program Manager | Data Collection, administration, coordination, sites, program delivery | 16,000 |

Project timeline
The project will begin July 1, 2020, or as soon as the contract with the City of Vallejo is completed, and will continue over a one year period. Activities for each quarter are detailed below.

| ACTIVITY | Q1 | Q2 | Q3 | Q4 |
| --- | --- | --- | --- | --- |
| 07/01/2020 Upon award, enter into a contract agreement with Heat Time, a non-profit social justice organization and developer of the H.E.A.T. Program. Identify outcome measures and begin design of evaluation plan. |  |  |  |  |
| 07/15/2020 Schedule 3 Day Train the Facilitator Class for 10 staff and or community partners |  |  |  |  |
| 07/30/2020 Identify staff to be trained as facilitators |  |  |  |  |
| 09/15/2020 Heat Time staff conducts training |  |  |  |  |
| 09/30/2020 Probation Management identifies lead facilitator for the pilot 9 month program H.E.A.T. |  |  |  |  |
| 10/1/2020 Marketing and Client Engagement via flyers, presentations and conversations with clients |  |  |  |  |
| 10/15/2020 Begin 9 month H.E.A.T. Program with Probation Clients. |  |  |  |  |
| 10/30/2020 Schedule with Heat Time 3-4 on site, at least quarterly, Coaching and Fidelity sessions for Program Facilitators. |  |  |  |  |
| 11/1/2020 Finalize outcome measure and evaluation plan. |  |  |  |  |
| 06/30/2021 Program Completion and Graduation Ceremony |  |  |  |  |