| Expense Category | Description Assumes 50 Campers for 2 Weeks | Rate | Cost | Remarks | $40,000 |
| --- | --- | --- | --- | --- | --- |
| Stipend | (1) Camp Coordinator | 1 X 100 hrs @ $35 p/h | $3,500 | Short Duration- Local Hire |  |
|  | (4) Camp Counselors | 4 X 100 hrs @ $25 p/h | $10,000 | Short Duration- Local Hires |  |
|  | (14) Camp Artists | 16 hrs p/d X 10 days @ $30 per hr | $4,800 | Short Duration Local Artists with specialized skills |  |
|  | (1) Special Guest Artist | Flat Fee | $1,500 | Specific Talent Related toTheme |  |
|  |  |  | $19,800 |  | $20,200 |
| Temporary Venue Fee | Location to conduct Camp (TBD) | Flat Rate | $3,000 | Square footage adequate for 50 |  |
|  |  |  | $3,000 |  | $17,200 |
| Camp Supplies | Easels, work tables, chairs, brushes, tools, digital equipment, robotic parts, storage containers, display hardware, lighting, set materials |  | $4,200 | Durable |  |
| Camp Supplies | Paint, pencils, pastels, paper, clay, glaze, tile, canvas, materials, fabric, ink, wood, glue, clean up products and other art related goods |  | $9,425 | Expendable |  |
|  |  |  | $13,625 |  | $3,575 |
| Misc Camp Related Expenditures | Web Design and update, Advertising & Outreach, Camper T-Shirts, Field Trip Transportation, Celebration Luncheon, Camper Water and Snacks |  |  | Web design includes camp application site. Transportation is provided by a licensed and insure company |  |
|  |  |  | $3,575 |  | $0 |

This budget only shows costs allowable under Participatory Budgeting guidelines.  All other associated expenses related to conducting the Camp will be paid for by VCAF.  VCAF as a non-profit entity cannot derive a profit from any activity.  Their contribution for a Camp consisting of 50 Campers (approximate cost of $50,000) will be well over $10,000 and hundreds of hours of volunteer time.

Timeline for 2020 Camp Implementation

All activities performed before July 2020 will be conducted by unpaid Volunteers in coordination with Vallejo Community Arts Foundation.

| Nov 19 | Begin planning process |
| --- | --- |
| Dec 19 | Solicit Interest from Community. Confirm Theme for Visions of the Wild Festival |
| Jan 20 | Determine Artists, Counselors and Volunteers |
| Feb 20 | Identify Venue Location and Design Camp Schedule |
| Mar 20 | Create Supply and Materials List |
| Apr 20 | Advertise and Fundraise |
| May 20 | Confirm Commitments and Identify Campers |
| Jun 20 | Purchase Supplies and Layout Camp Configuration |
| Jul 20 | Conduct 2 Week Camp for 50 Children |