| Expense Category | Description Assumes 60 Campers for 2 Weeks | Rate | Cost | Remarks | $40,000 |
| --- | --- | --- | --- | --- | --- |
| Stipend | (1) Camp Coordinator | 1 X 100 hrs @ $35 p/h | $3,500 | Short Duration- Local Hire |  |
|  | (4) Camp Counselors | 4 X 100 hrs @ $25 p/h | $10,000 | Short Duration- Local Hires |  |
|  | (14) Camp Artists | 16 hrs p/d X 10 days @ $30 per hr | $4,800 | Short Duration Local Artists with specialized skills |  |
|  | (1) Special Guest Artist | Flat Fee | $1,500 | Specific Talent Related toTheme |  |
|  |  |  | $19,800 |  | $20,200 |
| Temporary Venue Fee | Location to conduct Camp (TBD) | Flat Rate | $3,000 | Square footage adequate for 60 |  |
|  |  |  | $3,000 |  | $17,200 |
| Camp Supplies | Easels, work tables, chairs, brushes, tools, digital equipment, robotic parts, storage containers, display hardware, lighting, set materials |  | $4,200 | Durable |  |
| Camp Supplies | Paint, pencils, pastels, paper, clay, glaze, tile, canvas, materials, fabric, ink, wood, glue, clean up products and other art related goods |  | $9,425 | Expendable |  |
|  |  |  | $13,625 |  | $3,575 |
| Misc Camp Related Expenditures | Web Design and update, Advertising & Outreach, Camper T-Shirts, Field Trip Transportation, Celebration Luncheon, Camper Water and Snacks |  |  |  |  |
|  |  |  | $3,575 |  | $0 |

Timeline for 2020 Camp Implementation

All activities performed before July 2020 will be conducted by unpaid Volunteers in coordination with Vallejo Community Arts Foundation.

| Nov 19 | Begin planning process |
| --- | --- |
| Dec 19 | Solicit Interest from Community. Confirm Theme for Visions of the Wild Festival |
| Jan 20 | Determine Artists, Counselors and Volunteers |
| Feb 20 | Identify Venue Location and Design Camp Schedule |
| Mar 20 | Create Supply and Materials List |
| Apr 20 | Advertise and Fundraise |
| May 20 | Confirm Commitments and Identify Campers |
| Jun 20 | Purchase Supplies and Layout Camp Configuration |
| Jul 20 | Conduct 2 Week Camp for 60 Children |