- Project Budget

| Budget Item | # Needed | Cost | Total |
| --- | --- | --- | --- |
| Coaches Salary (5 middle school sites total) | 1 Coach per middle school site-5 total | $14 per hour x 36 hours x 10 months (Aug 2021-June 2022) x 5 coaches | $25,200 |
| Assistant Coaches (total 5 Highschool students) | 1 Coach per middle school site-5 total | $8 per hour x 36 hours x 10 months (Aug 2021-June 2022) x 5 assistant coaches | $14,400 |
| Uniforms per student (20 students x 5 middle schools) | 100 students | 20 students per school x 5 schools @ $100.00 cost of each uniform | $10,000.00 |
| Equipment (1 set of tools consist of -flags, flag pole, flag bag, saber, rifle, school t-shirt) | 1 colorguard equipment bundle per student – 100 students total | $200 per equipment bundle | $20,000.00 |
| Transportation | 5 scheduled dates (tbd) | Round trip $225 estimate in town for the rental of a Bus | $1125.00 |
| Transportation | 3 scheduled dates (tbd) | Round trip $1200 estimate out of town trip for the rental of a Bus | $3600.00 |
| GRAND TOTAL: |  |  | $ 74,325.00 |

- Project timeline

The project will begin July 1, 2020, or as soon as the contract with the City of Vallejo is completed, and will continue over a one year period. Activities for each quarter are detailed below.

| ACTIVITY | Q1 JUL 2020-SEPT 2020 | Q2 OCT 2020-DEC 2020 | Q3 JAN 2021-MAR 2021 | Q4 APR 2021-JUN 2021 |
| --- | --- | --- | --- | --- |
| Coach/Assistant coach Recruitment and Hiring Process | X |  |  |  |
| Contract signingVUSD/ School site designation/Program Design and Calendar of events for Colorguard completed Budget review/ |  | X |  |  |
| Marketing/Advertisement to parents and school sites/Try outs and Auditions scheduled/ Uniform and Equipment orders begin Sizes determined by size chart and order submission forms completed by students and coaches |  |  | X |  |